## Sprint 3
Workflow Progression
Day | Planned To-do | Actual To-do
2 | 3 | 3
3 | 2.4 | 3
4 | 1.8 | 3
5 | 1.2 | 3
6 | 0.6 | 3
7 | 0 | 3
Note: Ref. Phase 1 on why sprint starts on day 2.
Note 2: Despite being listed as a Sprint, very
little concrete work was done in this week,
due to team member sickness and other
factors.